## ProjectTimeline
AJAX GAME PROJECT ROADMAP
{42}
Project Timeline Template
© 2017 Vertex42 LLC
| Project Start | 01/15/2022
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple
Concept Phase | Analysis | 2022-01-15 | 2022-01-31 | Blue | 2022-01-15 | 16 | 0 | 0 | 0 | 0 | 0
| Story & World Creation | 2022-01-31 | 2022-02-15 | Blue | 2022-01-31 | 15 | 0 | 0 | 0 | 0 | 0
| Firsts Charecters Desings | 2022-01-31 | 2022-02-15 | Blue | 2022-01-31 | 15 | 0 | 0 | 0 | 0 | 0
| Story Board | 2022-02-15 | 2022-02-28 | Blue | 2022-02-15 | 13 | 0 | 0 | 0 | 0 | 0
Design Phase | Script | 2022-03-01 | 2022-03-15 | Purple | 2022-03-01 | 0 | 0 | 0 | 0 | 0 | 14
| Music | 2022-03-01 | 2022-05-15 | Purple | 2022-03-01 | 0 | 0 | 0 | 0 | 0 | 75
| Designs Charecters and World | 2022-03-01 | 2022-05-15 | Purple | 2022-03-01 | 0 | 0 | 0 | 0 | 0 | 75
| Code Design | 2022-03-01 | 2022-03-15 | Purple | 2022-03-01 | 0 | 0 | 0 | 0 | 0 | 14
Production Phase | Production | 2022-03-15 | 2022-06-15 | Green | 2022-03-15 | 0 | 0 | 92 | 0 | 0 | 0
|  | 2022-01-15 | 2021-01-31 | Green | 2022-01-15 | 0 | 0 | -349 | 0 | 0 | 0
|  | 2022-01-15 | 2021-02-01 | Green | 2022-01-15 | 0 | 0 | -348 | 0 | 0 | 0
|  | 2022-01-15 | 2021-02-02 | Green | 2022-01-15 | 0 | 0 | -347 | 0 | 0 | 0
Test Phase | Serch For Testers | 2022-06-01 | 2022-06-15 | Brown | 2022-06-01 | 0 | 0 | 0 | 14 | 0 | 0
| Testing Phase | 2022-06-15 | 2022-06-30 | Brown | 2022-06-15 | 0 | 0 | 0 | 15 | 0 | 0
| Solve Errors | 2022-06-15 | 2022-07-15 | Brown | 2022-06-15 | 0 | 0 | 0 | 30 | 0 | 0
Marketing Phase | Creating an IG | 2022-05-15 | 2022-05-31 | Orange | 2022-05-15 | 0 | 0 | 0 | 0 | 16 | 0
| Showing our work in pages | 2022-05-15 | 2022-05-31 | Orange | 2022-05-15 | 0 | 0 | 0 | 0 | 16 | 0
| Making a Website | 2022-05-15 | 2022-06-15 | Orange | 2022-05-15 | 0 | 0 | 0 | 0 | 31 | 0
Documentation | Documentate TFG | 2022-01-15 | 2022-07-31 | Red | 2022-01-15 | 0 | 197 | 0 | 0 | 0 | 0
Insert new rows above this one
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Milestone 1 | 2017-03-02 | 0.5 | 0.95
| Milestone 2 | 2017-04-01 | 0.25 | 0.95
| Milestone 3 | 2017-05-04 | 0.1 | 0.95
| Milestone 4 |  | 0.3 | 0.95
Formulas:
Start = IF(ISBLANK([START]),0,[START])
Blue = IF(ISBLANK([END]),0,IF([COLOR]=G43,DAYS([END],[START]),0))

## (c)
Project Timeline Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet